## Cover Page
Resource Plan Cover Page
Project name | Corporate campaign management
Project ID | P0023-2019
Brief description | The goal of the project is to enhance the SME campaign management processes and system functionality. The scope includes the top prirority demands from SME department. The solution is based on the existing XXX application.
Start date | 2019.03.04
End date | 2019.12.28
Sponsor | Chief Marketing Officer
Project Manager | Gerald Tembler
Total Man Days | 900
Total Human Resource Cost | 337710
Total Other Resource Cost | 370900
Total Resource Cost | 708610

## Instructions
Resource Plan - Instructions
The Resource Plan includes information of all necessary resources. Keep it updated during the project. There is some information entered for illustrative purposes. These figures are not comprehensive and don't reflect any real project information.
Human Resources sheet All internal and external human resources. Other Resources sheet All non-human resources, including material, equipment, and services Definitions sheet Definition of the datasheet columns in the 'Human Resources' and the 'Other Resources' sheets, also including the data validation value sets if any Data Validation sheet The value sets of the drop-down list that you can use on the data entry sheets. Feel free to add, delete, modify any of the elements.
upify IT Ltd. provides benchmarks, tools, recommendations, plans and other documents based on experience and knowledge gained during decades of experience in various IT top management positions. upify IT Ltd. disclaims responsibility or liability for any injury, damages, loss of opportunity, whether direct, indirect, consequential, special, incidental or exemplary, resulting from the use of its tools, plans, recommendations, articles or any other documents. All information is provided “as is” without any guarantee for results, completeness, and correctness and of any kind whatsoever, express or implied. Please adjust this and other upify IT Ltd. documents according to your particular situation, strategy, prioritization, organization, processes and any other circumstances that are relevant to you.
© upify IT Ltd. 2018 - All rights reserved - www.upifyit.com

## Human Resources
List of Human Resources
ID | Role | Deliverable | Expertise | Qualifications | Soft skills | Internal / External | Department / Company | Name | Commitment status | Estimation quality | Total PD | PD Rate | Cost | Requested Person Days (PD)
| Role |  | Seniority | Qualifications | Qualifications |  | Department | Propose name | Status |  | Total MD | MD Cost | Cost | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01
[14 empty] | 21 | 22 | 23 | 20 | 23 | 22 | 21 | 23 | 21 | 22
1 | Project Manager |  | C - Expert | PMP | Emotional intelligence | I - Internal | PMO | Tamara Glenn | C - Confirmed | H - High | 204 | 440 | 89760 | 21 | 22 | 23 | 20 | 13 | 22 | 21 | 23 | 21 | 18
2 | Project PMO lead |  | A - Junior |  | Precise | T - TBD | PMO or XYZ Ltd. | - | A - Planned | H - High | 76 | 440 | 33440 | 18 | 19 | 11 | 10 | 0 | 0 | 3 | 7 | 8 | 0
3 | Business Analyst |  | B - Intermediate |  | Communication | I - Internal | Processes | Denis Taylor | A - Planned | H - High | 76 | 440 | 33440 | 18 | 19 | 11 | 10 | 0 | 0 | 3 | 7 | 8 | 0
4 | Java Programmer |  | C - Expert | Cerfified |  | I - Internal | IT | - | C - Confirmed | M - Medium | 111 | 380 | 42180 | 0 | 0 | 5 | 20 | 23 | 10 | 10 | 23 | 10 | 10
5 | Java Programmer |  | B - Intermediate |  |  | E - External | ABC Ltd. | - | B - In alignment | M - Medium | 103 | 450 | 46350 | 0 | 0 | 5 | 20 | 21 | 7 | 7 | 23 | 10 | 10
6 | Java Programmer |  | B - Intermediate |  |  | T - TBD | IT or ABC Ltd. | - | D - Declined | L - Low | 103 | 280 | 28840 | 0 | 0 | 5 | 20 | 21 | 7 | 7 | 23 | 10 | 10
7 | Test Manager |  | C - Expert |  |  | I - Internal | IT | Tom Becker | C - Confirmed | M - Medium | 110 | 310 | 34100 | 0 | 0 | 0 | 5 | 12 | 12 | 19 | 20 | 20 | 22
8 | End User Tester |  | B - Intermediate |  |  | I - Internal | SME | - | B - In alignment | M - Medium | 56 | 180 | 10080 | 0 | 0 | 0 | 0 | 6 | 6 | 12 | 12 | 12 | 8
9 | System admin |  | B - Intermediate | CISA |  | I - Internal | IT | - | B - In alignment | H - High | 61 | 320 | 19520 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 12 | 12 | 12
10 | [10 empty] | 0 |  | 0
11 | [10 empty] | 0 |  | 0
12 | [10 empty] | 0 |  | 0
13 | [10 empty] | 0 |  | 0
14 | [10 empty] | 0 |  | 0
15 | [10 empty] | 0 |  | 0
16 | [10 empty] | 0 |  | 0
| Total | [9 empty] | 900 |  | 337710 | 57 | 60 | 65 | 110 | 101 | 69 | 87 | 150 | 111 | 90
Note on T6: Improve ITM Ltd.: Planned Holiday

## Other Resources
ID | Name | Description | Volume | Unit price | Opex | Capex | Status
1 | Server units |  | 32 | 1200 |  | 38400 | A - Planned
2 | Data Center LAN | LAN within the primary and backup data center that are needed for new equipments | 1 | 12000 |  | 12000 | C - Confirmed
3 | Storage unit |  | 12 | 24000 |  | 288000 | B - In alignment
4 | Seats in project office |  | 65 | 380 | 24700 |  | C - Confirmed
5 | Office supply |  | 65 | 120 | 7800 |  | C - Confirmed
6 |  |  |  |  | 0 | 0
7 |  |  |  |  | 0 | 0
8 |  |  |  |  | 0 | 0
9 |  |  |  |  | 0 | 0
10 |  |  |  |  | 0 | 0
11 |  |  |  |  | 0 | 0
12 |  |  |  |  | 0 | 0
13 |  |  |  |  | 0 | 0
14 |  |  |  |  | 0 | 0
15 |  |  |  |  | 0 | 0
16 |  |  |  |  | 0 | 0
|  |  | Total Opex: |  | 32500
|  |  | Total Capex: |  |  | 338400
|  |  |  | Total | 370900

## Definitions
'Human Resources' sheet
Column | Description | Data validation
ID | Unique identifier of the requested resource | -
Role | The role in the project | -
Deliverable | Brief description of the expected deliverable. In many cases, the deliverable will be the result of a team-work. | -
Expertise | Expertise level of the person. The definition of the grades (e.g., Junior, Intermediate, Expert) depends on the organizational specifics. For example, it may be a mixture of the number of years of experiences, the difficulty of tasks performed, and personal achievements so far. | A - Junior B - Intermediate C - Expert
Qualifications | Text field for the requested qualifications | -
Soft skills | Description of required soft skills. Some examples are team player, resilient, manages uncertainties, emotional intelligence. | -
Internal / External | Describes if the resource internal or external is. During the preparation phase, the value can be TBD as well, but the final plan should include the confirmed Internal or External value | I - Internal E - External T - TBD
Department / Company | The unit of the resource. In case of Internal, it is the name of the department. In case of external, it is the name of the external partner. During the preparation phase, the value can be empty, but the final plan should include the confirmed department for the Internals and the name of the company for the Externals | -
Name | The name of the person. During the planning, it may include the name of the proposed person. In the final version, this is the name of the confirmed person | -
Assignment status | The status of the alignment with the resource owner department or the external partner. During the planning, all values are possible. The final version should include only 'C - Confirmed' status; otherwise, the commitments are not final. | A - Planned B - In alignment C - Confirmed D - Declined
Estimation quality | The quality of the estimations. In some case it is rather precise, in other cases, it is not possible to make a reliable estimation, especially at the beginning of the project. | L - Low M - Medium H - High
Total PD | The total Person Days that are requested from the resource. It is the sum of the monthly Person Day requirement columns | -
PD rate | The daily Person Day rate of the human resource. For externals, this the contracted value. For internals, usually, the Controlling department of the organization sets this value for cost allocation. | -
Cost | Total cost of the resource, it is the PD rate multiplied by the total PD | -
Requested Person Days (PD) | The number of requested days for each month. It means the total volume for the month. It is possible that a part-timer works ten days in a month, spending each day half the time in the project. Line #4 includes the total working day in the month, please update according to months and local regulation. The color codes indicate the utilization as follows: - white: utilization = 0 - gray: 0 < utilization < = 20% - green: 20% < utilization < = 80% - gray: 80% < utilization < = 100% Please update the color codes with Home / Conditional formatting function as you prefer. Please update the Data / Data validation settings as you prefer | -
'Other Resources' sheet
Column | Description | Data validation
ID | Unique identifier of the requested resource | -
Name | Name of the requested resource
Description | Brief description of the requested resource
Volume | Volume in any unit that applies to the resource
Unit price | The price of the unit that is the same unit which is used in the Volume field
Opex | Operational expenditure part of the cost that is calculated as the Unit price multiplied by the Volume. The external regulations and the internal accounting policies determine if the spending Opex is.
Capex | Capital expenditure part of the cost that is calculated as the Unit price multiplied by the Volume. The external regulations and the internal accounting policies determine if the spending Capex is.
Status | The status of the alignment with the resource owner department or the external partner. During the planning, all values are possible. The final version should include only 'C - Confirmed' status; otherwise, the commitments are not final. | A - Planned B - In alignment C - Confirmed D - Declined

## Data Validation
Expertise | Internal / External | Assignment status | Estimation quality
A - Junior | I - Internal | A - Planned | L - Low
B - Intermediate | E - External | B - In alignment | M - Medium
C - Expert | T - TBD | C - Confirmed | H - High
D - Declined